## Gantt Chart-C조 - Table 1
4차산업 사물인터넷(iot) 시스템개발자 양성 과정 - 전원일기 조 |  |  |  |  | Try Smartsheet for FREE
PROJECT TITLE |  | PROJECT MANAGER
스마트팜 |  | 공통
COMPANY NAME |  | PROJECT START DATE
한국직업능력교육원 안산 |  | 2023-01-19 | 3 | <–– DO NOT DELETE OR ALTER CELL
[10 empty] | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11
TASK TITLE | TAKE SKILL | TASK OWNER | PCT OF TASK COMPLETE | SCHEDULED START | SCHEDULED FINISH | ACTUAL START | ACTUAL FINISH | FINISH VARIANCE | DURATION IN DAYS | 2023-01-16 | 2023-01-23 | 2023-01-30 | 2023-02-06 | 2023-02-13 | 2023-02-20 | 2023-02-27 | 2023-03-06 | 2023-03-13 | 2023-03-20 | 2023-03-27
프로젝트 진행 및 문서 작성 |  | 공통 | 81.67% | 2023-01-19 | 2023-03-10 | 2023-01-19 | 2023-03-31 | 15 | 52 | ftr | ftr | ftr | ftr | ftr | ftr | ftr | fntr | fntr | fntr | entr
주제 구상 |  | 공통 | 100% | 2023-01-19 | 2023-01-23 | 2023-01-19 | 2023-01-23 |  | 3 | ftr | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr
플로우 차트 제작 | gitmind | 공통 | 100% | 2023-01-23 | 2023-01-24 | 2023-01-23 | 2023-01-24 |  | 2 | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr
파츠리스트 제작 | excel | 공통 | 100% | 2023-01-25 | 2023-01-27 | 2023-01-25 | 2023-01-27 |  | 3 | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr
간트 차트 제작 | excel | 공통 | 100% | 2023-01-27 | 2023-02-01 | 2023-01-27 | 2023-02-06 | 3 | 7 | entr | ftr | fntr | entr | entr | entr | entr | entr | entr | entr | entr
전체 코드 통합 및 리뷰 | Python, C언어, MariaDB | 공통 | 90% | 2023-03-01 | 2023-03-03 | 2023-03-15 | 2023-03-22 | 13 | 6 | entr | entr | entr | entr | entr | entr | entr | entr | fntr | entr | entr
포트폴리오 작성 | 한글,word | 공통 | 0% | 2023-03-06 | 2023-03-10 | 2023-03-23 | 2023-03-31 | 15 | 7 | entr | entr | entr | entr | entr | entr | entr | entr | entr | fntr | entr
라즈베리 파이 서버 구축 |  | 이태현 | 100% | 2023-02-01 | 2023-02-20 | 2023-01-23 | 2023-02-17 | -3 | 20 | entr | fntr | ftr | ftr | etr | entr | entr | entr | entr | entr | entr
리눅스 설치 및 초기 세팅 | Linux(Raspberry Pi OS) | 이태현 | 100% | 2023-02-01 | 2023-02-02 | 2023-01-23 | 2023-01-24 | -9 | 2 | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr
필요 프로그램 설치 | Python,Flask,MariaDB | 이태현 | 100% | 2023-02-03 | 2023-02-06 | 2023-01-25 | 2023-01-26 | -9 | 2 | entr | entr | etr | entr | entr | entr | entr | entr | entr | entr | entr
DB 설계 및 프로그래밍 | MariaDB | 이태현 | 100% | 2023-02-06 | 2023-02-09 | 2023-02-06 | 2023-02-15 | 4 | 8 | entr | entr | entr | fntr | entr | entr | entr | entr | entr | entr | entr
라이브 스트리밍 서버페이지 구축 | Flask,OpenCV2 | 이태현 | 100% | 2023-02-10 | 2023-02-15 | 2023-02-15 | 2023-02-17 | 2 | 3 | entr | entr | entr | etr | entr | entr | entr | entr | entr | entr | entr
센서 값 시각화 서버페이지 구축 | Flask,MariaDB | 이태현 | 100% | 2023-02-16 | 2023-02-20 | 2023-02-15 | 2023-02-17 | -3 | 3 | entr | entr | entr | entr | etr | entr | entr | entr | entr | entr | entr
센서 설계 및 제어 |  | 김명석, 정준호 | 100% | 2023-01-23 | 2023-02-24 | 2023-01-23 | 2023-03-02 | 4 | 29 | entr | ftr | ftr | ftr | ftr | fntr | entr | entr | entr | entr | entr
회로 설계 및 제작 |  | 정준호 | 100% | 2023-01-23 | 2023-02-10 | 2023-01-23 | 2023-02-07 | -5 | 12 | entr | ftr | ftr | entr | entr | entr | entr | entr | entr | entr | entr
RasberraPI-Atmega 통신 코드 작성 및 테스트 |  | 김명석(정),정준호(부) | 100% | 2023-02-13 | 2023-02-17 | 2023-02-08 | 2023-02-17 |  | 8 | entr | entr | entr | fntr | entr | entr | entr | entr | entr | entr | entr
각종 센서 제어 및 테스트 | C언어 | 김명석(정),정준호(부) | 100% | 2023-02-20 | 2023-02-24 | 2023-02-20 | 2023-03-02 | 4 | 9 | entr | entr | entr | entr | entr | fntr | entr | entr | entr | entr | entr
센서 값 시각화 및 제어 |  | 김명석 | 100% | 2023-02-24 | 2023-03-27 | 2023-03-03 | 2023-03-14 | -11 | 8 | entr | entr | entr | entr | entr | etr | ftr | ftr | etr | etr | entr
PyQT 코드 작성 및 테스트 |  | 김명석 | 100% | 2023-02-24 | 2023-03-27 | 2023-03-03 | 2023-03-12 | -12 | 6 | entr | entr | entr | entr | entr | etr | ftr | ftr | etr | etr | entr
운영체제 쉘 스크립트 수정 |  | 김명석 | 100% | 2023-02-28 | 2023-03-01 | 2023-03-13 | 2023-03-14 | 9 | 2 | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr
실제 모델 제작 |  | 이태현,김명석 | 100% | 2023-01-26 | 2023-02-28 | 2023-01-26 | 2023-03-14 | 10 | 34 | entr | ftr | ftr | ftr | ftr | ftr | fntr | fntr | entr | entr | entr
스마트팜 외관 설계 |  | 김명석(정),이태현(부) | 100% | 2023-01-26 | 2023-01-28 | 2023-01-26 | 2023-01-30 | 0 | 3 | entr | fntr | entr | entr | entr | entr | entr | entr | entr | entr | entr
스마트팜 제작 및 조립 |  | 김명석(정),이태현(부) | 100% | 2023-02-01 | 2023-02-17 | 2023-02-01 | 2023-02-17 |  | 13 | entr | entr | ftr | ftr | entr | entr | entr | entr | entr | entr | entr
스마트팜 내부 센서 테스트 | C언어 | 김명석(정),이태현(부) | 100% | 2023-02-20 | 2023-02-24 | 2023-03-03 | 2023-03-08 | 8 | 4 | entr | entr | entr | entr | entr | entr | fntr | entr | entr | entr | entr
스마트팜 데코레이션 | blender | 이태현 | 100% | 2023-02-27 | 2023-02-28 | 2023-03-10 | 2023-03-14 | 10 | 3 | entr | entr | entr | entr | entr | entr | entr | fntr | entr | entr | entr
동영상 제작 |  | 정준호 | 0% | 2023-03-01 | 2023-03-03 | 2023-03-27 | 2023-03-29 | 18 | 3 | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr
제작과정 동영상 편집 | powerDerecter | 정준호 | 0% | 2023-03-01 | 2023-03-03 | 2023-03-27 | 2023-03-29 | 18 | 3 | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr
[10 empty] | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr
[10 empty] | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr
[10 empty] | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr
[12 empty] | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr
[12 empty] | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr
[10 empty] | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr
[10 empty] | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr | entr